Guide 2. Development Project APT

Assignature Capstone

1. Resume APT Project

| Project Progress | Our APT project has progressed with the definition and development of the main components of the proposed solution. So far, we have completed: - Definition of general and specific objectives, aligned with the identified problem. - Initial design work including solution architecture, data model, and user flows. - Preliminary implementation of backend and frontend, with basic integration of key functionalities. - Partial documentation, such as meeting minutes and a work log. These advances demonstrate compliance with the specific objectives for this stage, especially the validation of the design and the initial implementation of the solution. |
| --- | --- |
| Objectives | The general objective remains the same as defined in Phase 1. Minor adjustments were made to the specific objectives to emphasize early prototype validation and database integration. |
| Methodology | The methodology followed is traditional, structured over 15 weeks. It is divided into three partial deliveries that allow monitoring of progressive progress, and a fourth instance corresponding to the final defense of the project. The main adjustment was to strengthen the scheduling of activities around these milestones, ensuring that each phase includes specific deliverables (documentation, functional prototype, testing) that facilitate both internal control and external evaluation. |
| Progress Evidence | - Screenshots and code of the first developed modules. - Updated diagrams of architecture and data model. - Backlog records with completed and ongoing tasks. These evidences prove that the project is progressing as planned, since they show both the technical work (design and implementation) and the organizational aspects (management of plan and methodology). |

Work Plan

| Competence or unit of competence | Activity | Resources | Duration | Responsible | Observations | Progress status | Adjustments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Systems analysis and design | Requirements gathering and definition of objectives | Meetings, interviews, documentation tools | 2 weeks | Full team | Initial user information collected | Completed | None |
| Solution design | Solution architecture and data model | Modeling tools (Draw.io, SQL Server, etc.) | 3 weeks | Member A | Diagrams and initial DB created | In progress | Adjusted after teacher feedback |
| Software development | Backend implementation in .NET 8 | Visual Studio, SQL Server | 3 weeks | Member B | APIs in development | In progress | Minor adjustments in endpoints |
| Software development | Frontend implementation in React | Vite, React, UI libraries | 3 weeks | Member C | Login and main screens advanced | In progress | Modified components after feedback |
| Project management | Monitoring and coordination meetings | Minutes, Trello, calendar | Entire semester | Full team | Good coordination | In progress | None |
| Quality assurance | Unit, integration, and usability testing | Postman, Jest, test users | 2 weeks | Member D | Unit tests not started yet | Not started | Rescheduled to week 10 |
| Documentation | User manual and technical docs | Word, GitHub | 1 week | Member A | Draft in progress | Not started | Planned for week 12 |
| Final presentation | Preparation and defense | PowerPoint, functional prototype | 1 week | Full team | To be prepared in final week | Not started | None |

3. Adjustments from Monitoring

Facilitating and hindering factors: The traditional methodology structured around partial deliveries has facilitated progress monitoring and team coordination. Weekly meetings have also played a key role in keeping tasks aligned. Main difficulties were related to time availability of team members due to other academic and work responsibilities. To mitigate this, we set a detailed schedule of milestones and redistributed tasks according to workload

Adjusted or eliminated activities Unit and integration testing were shifted from week 8 to week 10, once the first stable version of the backend and frontend was consolidated. No activities were eliminated, but documentation was reinforced to be developed in parallel with implementation instead of only at the end.

Activities not started or delayed: Documentation and final defense preparation have not been started yet since they correspond to later phases. Testing has a slight delay, as efforts focused first on consolidating the development modules. To address this, test case design will be prioritized in parallel with remaining development so execution starts in week 10 without major impact.