Guide 3. Final Inform Project APT

Assignature Capstone

1. Final Inform Project APT

| Project Name | MediTriage. |
| --- | --- |
| Performance area(s) | Software development. Project management in IT. Systems analysis and design. |
| Competences | - Design and implement technological solutions according to functional and non-functional requirements. - Apply project management methodologies to plan, execute and evaluate software solutions. - Use programming tools, databases, and frameworks for application development. |

| Contents of Final Inform |  |
| --- | --- |
| 1. Relevance of the APT Project | The project aimed to solve the lack of specialized platforms for selling and managing musical instruments, a field with growing demand but limited digitalization in some markets. This topic is relevant for the IT professional field because it combines web application development, non-relational database design (MongoDB), and the integration of e-commerce flows, all of which are highly demanded skills in the industry. The situation addressed is located in the Chilean context, with regional projection. It impacts both end users (musicians and instrument buyers) and administrators who need to manage stock, orders, and purchase statuses. The value contribution of the project is twofold: - Real: a functional e-commerce prototype with filters, user registration, and stock control. - Educational: strengthening professional competences in design, implementation, and IT project management. |
| 2. Objectives | General objective Develop a web e-commerce platform for musical instrument sales, ensuring stock control, user registration, and purchase order management. Specific objectives - Implement a registration and login system with email and password. - Develop a catalog that allows filtering instruments by category, price, and availability. - Incorporate stock control that prevents adding products to the cart when items are out of stock. Design an administrative portal to manage purchase orders, update stock, and track orders. - Integrate order statuses (pending and approved) to provide traceability of the purchase process. |
| 3. Methodology | The methodology applied was traditional, structured over 15 weeks. This approach divided the work into three partial deliveries to monitor progress, and a fourth milestone corresponding to the final defense. Phases and procedures: - Initial planning (weeks 1–2): definition of objectives, project scope, requirements identification, and schedule design. - Design (weeks 3–5): elaboration of system architecture, MongoDB data model, and user flow diagrams. - Development (weeks 6–11): implementation of backend in Python, frontend web development, database integration, and main functionalities (catalog, stock control, admin portal). - Testing and validation (weeks 12–13): functional and usability testing to ensure compliance with requirements. - Documentation (week 14): preparation of user manual and technical documentation. - Presentation and defense (week 15): preparation of the final presentation and defense before the evaluation committee. Relevance of the methodology The traditional approach was pertinent because it allowed for structured and controlled execution, ensuring each partial delivery represented a measurable milestone. It also supported compliance with deadlines and clarified responsibilities among team members. |
| 4. Development | Main activities - Planning: requirements gathering, objectives definition, and schedule creation. - Design: system architecture, database diagrams, and user flows. - Implementation: backend in Python and frontend in React, database integration, catalog, stock control, and admin portal. - Testing: functionality (catalog, login, stock validation, order management) and usability testing. - Documentation: user manual, technical documentation, meeting minutes. - Presentation: preparation and execution of the final defense. Facilitating factors - Structured planning with partial deliveries that clarified progress. - Collaborative tools (GitHub, Trello, Google Meet) that supported coordination. - Team motivation to build a functional prototype simulating a real e-commerce scenario. Difficulties - Limited availability of some team members due to academic and work commitments. - Adjustments in the data model, since the first version did not correctly link purchase orders and stock. - Delay in unit testing, postponed from week 8 to week 10. Adjustments made - Task redistribution to balance workloads. - Data model adjustments in MongoDB for better inventory/order logic. - Rescheduled testing to week 10, allowing validation with a stable system. |
| 5. Evidence | Collected evidence includes: - System screenshots: product catalog with filters, product detail with stock validation, admin portal for orders and inventory. - Source code: backend in Python with MongoDB, frontend in React with login and dynamic components. - Technical and user documentation: architecture diagrams, data model, and user manual. - Project records: updated schedule, backlog, and task progress logs. These items provide a comprehensive view of the project lifecycle, from planning and design to implementation and validation. |
| 6. Professional Interests and Projections | Reflection The project reinforced interest in designing and implementing technological solutions for real-world problems, especially in e-commerce. It clarified the importance of structured project management, as well as the integration of design, development, testing, and documentation. Initial professional interests remain, with stronger focus on IT project management and building solutions that create value for both users and organizations. Projections - Short to medium term: roles such as technical leader, project manager, or full-stack developer, applying skills in planning, coordination, and software development. - Medium to long term: specialization in software architecture and project management (traditional and agile), aiming to participate in large-scale projects in IT and digital commerce industries. |